# OpenShift 4.22 ACM Automation (Hub-Spoke, Nutanix)

## Kanban-Ready Task Cards

Repo: SkylarScaling/71638776-openshift-automation

How to use this document: each shaded box is a single kanban card — use the bolded text as the card title, and the "Acceptance criteria" line beneath it as the card description or Definition of Done. Phase and section headings map to suggested swimlanes/columns or epics (e.g., one column per Phase, or one epic per section, with cards moving through To Do → In Progress → Done).

# Phase 0 — Discovery & Planning

CARD: Confirm final cluster topology (hub-spoke, no Global Hub)

Acceptance criteria: Confirm final topology: single ACM Hub cluster per site + N managed clusters (no Regional Hub, no Global Hub) — document this explicitly in the design doc/SOW so it isn't re-litigated mid-project.

CARD: Verify OCP 4.22 support on Nutanix IPI

Acceptance criteria: Confirm target OpenShift version support: verify 4.22 is compatible with the installer/version logic baked into the roles, and check Red Hat's OCP 4.22 platform support matrix for Nutanix IPI specifically (platform support can lag behind AWS).

CARD: Review existing Nutanix IPI role structure

Acceptance criteria: Review the repo's existing Nutanix IPI role/variable structure (Prism Central/Element vars, subnet, VIP, and any load-balancer/DNS integration points) against this customer's environment to identify what's directly usable vs. what needs adaptation.

CARD: Confirm Nutanix environment structure

Acceptance criteria: Confirm Nutanix environment structure: single Prism Central managing all 5 sites vs. per-site Prism Central; Prism Element cluster(s), AHV version, and available compute/storage capacity per site.

CARD: Confirm networking model & LB approach per site

Acceptance criteria: Confirm networking model per site: VLAN/subnet for OpenShift nodes, DHCP vs. static IPs/reservations, and how API/Ingress VIPs will be fronted (customer LB such as F5/NSX-ALB, or MetalLB/kube-vip) — confirm which of these the repo's existing Nutanix role already supports vs. expects the customer to provide externally.

CARD: Confirm DNS ownership & automation per site

Acceptance criteria: Confirm DNS ownership per site: identify who creates/updates API, *.apps, and ingress DNS records for this customer, and whether the repo's existing Nutanix path automates that or expects it as a pre/post-install step.

CARD: Confirm Nutanix CSI storage class support

Acceptance criteria: Confirm storage: whether the repo's existing Nutanix path already wires up Nutanix CSI-backed storage classes for ODF, or whether that needs to be added.

CARD: Inventory customer-specific substitutions

Acceptance criteria: Inventory customer-specific substitutions needed: image registry (Quay vs. customer registry), GitOps repo host (customer GitHub/GitLab vs. public GitHub), SMTP relay, pull secret source.

CARD: Identify security & compliance requirements

Acceptance criteria: Identify customer security/compliance requirements (network segmentation, egress proxy requirements, logging/SIEM integration, change management process).

CARD: Define success criteria & acceptance tests

Acceptance criteria: Define success criteria and acceptance tests for "implemented and tested" vs. "production ready".

CARD: Establish RACI for 5-site rollout

Acceptance criteria: Establish RACI for the 5-site rollout (who owns Nutanix capacity/quota, DNS record creation, firewall change requests, on-call during cutover).

# Phase 1 — Cluster Prerequisites & Network/Firewall Validation

## 1.1 Nutanix Account, Capacity & Access

CARD: Validate Nutanix service account & permissions

Acceptance criteria: Validate a Nutanix service account/role exists with permissions to create VMs, images, networks, and categories via Prism Central API/Terraform provider, scoped appropriately for the automation (avoid using a full admin account where a scoped role suffices).

CARD: Confirm per-site compute/storage capacity

Acceptance criteria: Confirm compute/storage/memory capacity reserved per site is sufficient for the Hub cluster + all planned managed clusters (control plane, worker, and any infra/storage node pools) — there is no cloud-elastic quota to fall back on, so this must be sized up front per site.

CARD: Confirm RHCOS image handling approach

Acceptance criteria: Confirm the RHCOS image handling approach for Nutanix: image upload to Prism Central image service (via installer or pre-staged), and how that's refreshed for each OCP 4.22 z-stream update.

CARD: Provision subnets, VLANs & IP reservations

Acceptance criteria: Confirm subnet(s)/VLAN(s), IP ranges, and any static IP reservations (or DHCP scope) are provisioned per site for control plane, worker, and bootstrap nodes.

CARD: Reserve API & Ingress VIPs

Acceptance criteria: Confirm API and Ingress VIP addresses/DNS names are reserved per site and consistent with the load-balancer approach decided in Phase 0.

CARD: Confirm DNS record-creation access

Acceptance criteria: Confirm DNS zone/record-creation access is in place per site for API, *.apps wildcard (or explicit ingress records), so each site's base_domain resolves correctly before install.

## 1.2 Firewall / Egress Allow-List (least-privilege)

CARD: Validate Red Hat registry firewall rules

Acceptance criteria: Document and validate outbound access to Red Hat registries and services: registry.redhat.io, registry.access.redhat.com, quay.io, cdn.quay.io, cdn01/02/03.quay.io, sso.redhat.com, cert-api.access.redhat.com, api.access.redhat.com, console.redhat.com (telemetry/insights, if not disabled), mirror.openshift.com, api.openshift.com.

CARD: Validate customer image registry firewall rules

Acceptance criteria: Confirm final hostname(s) for the customer image registry once the registry substitution is implemented, and remove/replace default Quay dependency where the customer intends to run their own registry.

CARD: Validate customer Git host firewall rules

Acceptance criteria: The default Day 2 GitOps roles (apps_install_acm, apps_install_odf, apps_install_mco, apps_install_global_hub, apps_install_coo, apps_install_quay) point at SkylarScaling/gitops-install-* on public GitHub; validate firewall rules against the customer's actual repo host, not the public defaults.

CARD: Validate Prism Central firewall access

Acceptance criteria: Confirm Prism Central API endpoint(s) are reachable from the control node/installer, and confirm firewall/network segmentation between the control node's network and the Prism Central management network.

CARD: Validate/configure outbound proxy settings

Acceptance criteria: Confirm whether the customer's Nutanix clusters and OpenShift node network require an outbound proxy for internet-bound traffic (Red Hat registries, Git host), and if so, validate openshift-install and the automation's proxy configuration (httpProxy/httpsProxy/noProxy) rather than assuming direct egress.

CARD: Validate SMTP relay firewall rule

Acceptance criteria: Confirm firewall access to the SMTP relay host/port (smtp.host/smtp.port in inventory) for alerting.

CARD: Validate NTP firewall rule

Acceptance criteria: Confirm firewall access to required NTP sources.

CARD: Validate internal DNS resolver access

Acceptance criteria: Confirm firewall access to internal DNS resolvers.

CARD: Validate control-node egress rules

Acceptance criteria: Confirm control-node (Ansible/bootstrap host) egress rules match the same allow-list plus package/PyPI mirror access needed for ansible, kubernetes.core, ansible.posix, kubernetes, openshift, and any Nutanix SDK/provider dependencies.

CARD: Test deny-by-default firewall behavior

Acceptance criteria: Explicitly test and document deny-by-default behavior: attempt a connection to a non-allow-listed endpoint from a cluster node and confirm it is blocked.

CARD: Validate required ingress rules

Acceptance criteria: Validate ingress rules: control-node → cluster API/bootstrap, and any required inbound for load balancers/ingress per customer network design.

## 1.3 Credentials & Secrets Prerequisites

CARD: Obtain Red Hat pull secret

Acceptance criteria: Obtain/renew Red Hat pull secret (~/pull-secret.json from console.redhat.com) for the customer's Red Hat account.

CARD: Provision SSH keypairs

Acceptance criteria: Generate or provision SSH keypair(s) (~/.ssh/id_ed25519.pub) per site/control-node.

CARD: Define secure credential storage process

Acceptance criteria: Confirm process for storing Prism Central service-account credentials / SMTP app password securely (Ansible Vault, HashiCorp Vault, CyberArk, etc.) rather than committing to inventory in plaintext.

CARD: Confirm registry & Git credentials available

Acceptance criteria: Confirm customer image registry credentials and customer Git host credentials/tokens are available for automation use.

## 1.4 Control Node Setup

CARD: Provision control node(s)

Acceptance criteria: Provision control node(s) meeting local tool prerequisites (Python 3 + pip, Ansible).

CARD: Install required Ansible collections

Acceptance criteria: Run ansible-galaxy collection install kubernetes.core ansible.posix.

CARD: Run OCP prerequisites playbook

Acceptance criteria: Run ansible-playbook ocp/install-ocp-prerequisites.yaml --ask-become-pass from playbooks/ and confirm oc, openshift-install, required Python libs, and any Nutanix-specific CLI/SDK tooling install correctly.

CARD: Validate force_update binary refresh path

Acceptance criteria: Validate -e force_update=true path for refreshing binaries, and document when this should be used.

# Phase 2 — Implementation, Testing & Customization (Lab/Non-Prod Environment)

## 2.1 Nutanix Path — Code Review & Gap Analysis

CARD: Review existing Nutanix IPI automation logic

Acceptance criteria: Read through the repo's existing Nutanix IPI role/playbook logic (install-config.yaml generation, Prism Central/Element vars, subnet/VIP handling, DNS/LB integration points, storage class wiring) to build a shared understanding of what it does today.

CARD: Confirm prior OCP version test coverage

Acceptance criteria: Confirm which OpenShift version(s) the existing Nutanix path has been tested against previously, and identify any known gaps toward 4.22.

CARD: Map Nutanix variables to customer environment

Acceptance criteria: Map the existing Nutanix variable structure against this customer's environment (Prism Central/Element details, subnet, VIPs, DNS mechanism, LB approach) and flag any fields the customer's environment needs that aren't yet parameterized.

CARD: Confirm hub-spoke playbook invokes Nutanix path

Acceptance criteria: Confirm the two-tier hub-spoke-ipi-setup.yaml playbook correctly invokes the Nutanix path for both hub_cluster and managed_clusters groups (not just validated previously against a 3-tier layout, if that was the prior test history).

CARD: Confirm kubeconfig output path on Nutanix

Acceptance criteria: Confirm kubeconfig output path convention ({{ tmp_dir }}/acm-global-hub/install/{{ ocp_cluster.name }}/auth/kubeconfig) behaves the same on Nutanix as on AWS.

CARD: Document Nutanix automation gaps

Acceptance criteria: Document any genuine gaps found (e.g., DNS record creation not automated, LB integration assumes a specific product, storage class not wired to Nutanix CSI) as scoped work items rather than assumed blockers.

## 2.2 Close Identified Gaps

CARD: Implement DNS record automation (if needed)

Acceptance criteria: Implement/adjust any DNS record creation or hand-off step needed for this customer's DNS system — only if the gap analysis found this isn't already handled.

CARD: Implement LB integration (if needed)

Acceptance criteria: Implement/adjust load-balancer integration for API/Ingress VIPs to match the customer's chosen approach — only if the gap analysis found this needs customer-specific config rather than existing support.

CARD: Add/adjust Nutanix capacity pre-checks

Acceptance criteria: Confirm/adjust Nutanix capacity pre-checks (available vCPU/memory/storage per Prism Element cluster against planned node counts) exist or are added.

CARD: Confirm ODF uses Nutanix CSI storage classes

Acceptance criteria: Confirm ODF/storage role uses Nutanix CSI-backed storage classes correctly for this customer's Nutanix cluster configuration.

CARD: Add Nutanix CLI/SDK to prerequisites playbook

Acceptance criteria: Confirm install-ocp-prerequisites.yaml installs any Nutanix-specific CLI/SDK dependencies needed on the control node (e.g., Nutanix Terraform provider, ntnx CLI/SDK) alongside oc/openshift-install/Python libs.

## 2.3 Baseline Implementation & Validation (Nutanix, two-tier)

CARD: Build two-tier Nutanix inventory.yaml

Acceptance criteria: Build an inventory.yaml for the two-tier hub_cluster / managed_clusters topology (no regional_hubs group) with openshift_version bumped to 4.22, using the existing Nutanix variable structure (Prism Central/Element details, subnet, VIPs).

CARD: Run tier1 (Hub) install in lab

Acceptance criteria: Run hub-spoke-ipi-setup.yaml tagged tier1 only first in a Nutanix lab/non-prod environment, validate the ACM Hub comes up clean before proceeding.

CARD: Run tier2 (managed cluster) install in lab

Acceptance criteria: Run --tags tier2 --limit <managed-cluster> to add a single managed cluster, validate it registers correctly into the hub's spokes_clusterset.

CARD: Validate clusterset parent/child matching

Acceptance criteria: Validate parent_clusterset on each managed cluster matches the hub's spokes_clusterset exactly (common misconfiguration point).

CARD: Confirm kubeconfig output for all clusters

Acceptance criteria: Confirm kubeconfigs land at the expected path for every cluster and are usable.

## 2.4 Customization for Customer Environment

CARD: Implement image registry substitution

Acceptance criteria: Point Day 2 Quay/registry roles at the customer's image registry instead of default Quay install path, or confirm customer wants the repo's own Quay install (apps_install_quay → gitops-install-quay) and adjust accordingly.

CARD: Implement GitOps repo substitution

Acceptance criteria: Override default repo URLs in inventory/role vars for the Day 2 components in scope (ACM, ODF, MCO, COO, Quay — excluding the Global Hub component, which isn't used) to point at the customer's internal GitHub/GitLab org instead of SkylarScaling/gitops-install-*.

CARD: Fork & pin GitOps repos to customer Git host

Acceptance criteria: Fork/mirror the gitops-install-* repos into the customer's Git host, adapt any customer-specific policy/config in those repos, and pin acm_git_repo_revision / odf_git_repo_revision to appropriate branches/tags (not floating main for production).

CARD: Update SMTP alerting configuration

Acceptance criteria: Update SMTP settings (smtp.host, from_address, default_to, esp_to, app password) to customer's mail relay and alert routing.

CARD: Adjust VM sizing & replica counts

Acceptance criteria: Adjust install_config VM sizing (vCPU/memory/disk) and replica counts per tier to match customer's sizing/capacity requirements and available Nutanix cluster capacity.

CARD: Configure enable_uwm per cluster

Acceptance criteria: Decide and set enable_uwm per cluster based on whether customer runs user-namespace workloads needing monitoring (e.g., ArgoCD metrics).

CARD: Set gitops_version per managed cluster

Acceptance criteria: Set gitops_version consistently per managed cluster per customer's supported GitOps operator version (1.18 or 1.19).

CARD: Review node placement & redundancy settings

Acceptance criteria: Review node placement/redundancy settings per tier against customer's production requirements (e.g., spreading control plane across Prism Element hosts/blocks where the Nutanix cluster's fault-domain design allows it).

CARD: Disable Global Hub-only Day 2 role

Acceptance criteria: Confirm the Global Hub-only Day 2 role (argo/apps_install_global_hub) is disabled/excluded from the customized inventory and playbook path, since this deployment has no Global Hub tier.

CARD: Add customer-specific compliance/tagging automation

Acceptance criteria: Add/adjust any customer-required tagging, backup, or compliance automation not present in the base repo (document as extensions, keep changes isolated from upstream roles where possible for maintainability).

CARD: Version-control customized inventory & roles

Acceptance criteria: Version-control the customized inventory and any modified roles in the customer's own repo/branching strategy.

## 2.5 Testing

CARD: Run full functional test (hub + managed cluster)

Acceptance criteria: Functional test: full two-tier (hub + managed cluster) stand-up on Nutanix from a clean environment using the final customized inventory.

CARD: Run idempotency test

Acceptance criteria: Re-run playbooks against an already-provisioned environment, confirm no unintended changes/destructive actions.

CARD: Run targeted tier1/tier2 test

Acceptance criteria: Single-tier/targeted test: confirm --tags tier1 and --tags tier2 --limit <cluster> work in isolation against an existing hub.

CARD: Run failure/recovery test

Acceptance criteria: Simulate a failed managed-cluster provision and confirm re-run behavior and alerting via SMTP.

CARD: Run firewall validation test

Acceptance criteria: Run the full automation with only the allow-listed endpoints open (per Phase 1.2) and confirm no hidden dependencies on non-allow-listed hosts.

CARD: Run registry substitution test

Acceptance criteria: Confirm images pull correctly from customer registry (or Quay) with no fallback to public Red Hat registries where not intended.

CARD: Run GitOps substitution test

Acceptance criteria: Confirm ArgoCD Applications sync from customer's Git host and not the public default repos.

CARD: Run security review of secrets handling

Acceptance criteria: Confirm no secrets are logged in Ansible output/artifacts, credentials are sourced from vault/secrets manager, and pull secret/SSH key handling meets customer policy.

CARD: Run scale/timing test

Acceptance criteria: Measure end-to-end provisioning time per tier to inform production rollout scheduling and maintenance windows.

CARD: Run teardown/cleanup test

Acceptance criteria: Confirm a clean decommission path exists for lab clusters (important before repeating in 5 prod sites).

CARD: Write customer runbook documentation

Acceptance criteria: Capture a customer-specific runbook covering inventory structure, customization points, and known gotchas (Nutanix capacity sizing, clusterset matching, repo overrides, DNS/LB steps).

## 2.6 Sign-off

CARD: Conduct lab walkthrough/demo

Acceptance criteria: Walkthrough/demo of lab environment with customer stakeholders.

CARD: Obtain formal lab sign-off

Acceptance criteria: Formal sign-off on customized automation and firewall rule set before production rollout begins.

# Phase 3 — Production Rollout: 5 Sites

## 3.1 Per-Site Pre-Rollout Checklist (×5)

CARD: Confirm Nutanix access & capacity for site

Acceptance criteria: Confirm Nutanix Prism Central/Element access, service-account credentials, and capacity (vCPU/memory/storage) provisioned for this site.

CARD: Confirm networking & VIPs allocated for site

Acceptance criteria: Confirm subnet/VLAN, IP scheme (DHCP or static reservations), and API/Ingress VIPs are allocated for this site.

CARD: Confirm DNS readiness for site

Acceptance criteria: Confirm DNS records (or the process to create them) and base domain are ready to resolve for this site.

CARD: Submit firewall change request for site

Acceptance criteria: Submit and confirm firewall change request implementing the validated allow-list (Phase 1.2) for this site's network.

CARD: Provision site-specific credentials

Acceptance criteria: Confirm site-specific pull secret/SSH key/registry-credentials/Git-credentials are provisioned and stored securely.

CARD: Build site-specific inventory.yaml

Acceptance criteria: Build site-specific inventory.yaml from the customized template (site name, clusterset names, sizing, Nutanix cluster/subnet identifiers, SMTP recipients).

CARD: Schedule maintenance window for site

Acceptance criteria: Schedule maintenance window / change management approval for this site.

## 3.2 Per-Site Execution (×5)

CARD: Provision control node for site

Acceptance criteria: Provision control node for this site (or confirm shared control node has network access/credentials scoped for this site).

CARD: Run tier1 (Hub) install for site

Acceptance criteria: Run tier1 (this site's ACM Hub) and validate before proceeding.

CARD: Run tier2 (managed clusters) install for site

Acceptance criteria: Run tier2 (Managed Cluster(s)) and validate registration to the hub, GitOps sync, and monitoring data flow into the hub's Grafana.

CARD: Validate Day 2 components via ArgoCD

Acceptance criteria: Validate Day 2 components (ACM, ODF, MCO, COO, Quay/registry) all reconcile successfully via ArgoCD.

CARD: Run production firewall validation test

Acceptance criteria: Run firewall validation test again in production network (confirm allow-list is sufficient, no unplanned egress).

CARD: Confirm SMTP alerting for site

Acceptance criteria: Confirm alerting (SMTP) delivers to the correct on-call/recipient list for this site.

CARD: Hand off kubeconfig & RBAC to ops

Acceptance criteria: Confirm kubeconfig access and RBAC handed off correctly to customer's operations team for this site.

## 3.3 Per-Site Post-Go-Live (×5)

CARD: Validate observability/Grafana for site

Acceptance criteria: Validate observability: metrics from this site's managed clusters visible in this site's ACM Hub Grafana/dashboards.

CARD: Run acceptance tests for site

Acceptance criteria: Run acceptance tests defined in Phase 0 against this site.

CARD: Confirm backup/DR posture for site

Acceptance criteria: Confirm backup/DR posture (if in scope) for this site.

CARD: Document site-specific deviations

Acceptance criteria: Document any site-specific deviations from the standard inventory template.

CARD: Obtain customer sign-off for site

Acceptance criteria: Customer sign-off for this site.

## 3.4 Cross-Site Rollout Management

CARD: Define site rollout sequence

Acceptance criteria: Sequence the 5 sites (recommend: 1 pilot site first, validate fully, then remaining 4) rather than parallel first-time execution.

CARD: Conduct pilot-site retrospective

Acceptance criteria: After pilot site, conduct retrospective and fold any fixes back into the shared customized automation/roles before proceeding to remaining sites.

CARD: Track cross-site Nutanix capacity

Acceptance criteria: Track Nutanix capacity usage centrally if sites share a Prism Central instance, to avoid one site's deployment starving another's planned capacity.

CARD: Confirm pinned GitOps revisions per site

Acceptance criteria: Confirm each site's GitOps repo references point to correctly pinned revisions (not shared floating branches that could cause a change in one site to unintentionally affect another).

# Phase 4 — Handover & Closeout

CARD: Deliver final runbook

Acceptance criteria: Deliver final runbook covering: prerequisites, firewall allow-list, customized inventory structure, per-site rollout procedure, and rollback/teardown steps.

CARD: Deliver architecture diagram

Acceptance criteria: Deliver architecture diagram reflecting the customer's actual 5-site topology (hub/managed-cluster mapping per site, on Nutanix).

CARD: Conduct knowledge transfer session

Acceptance criteria: Knowledge transfer session with customer operations team.

CARD: Confirm customer self-service for new clusters

Acceptance criteria: Confirm customer owns and can independently re-run --tags tier2 --limit <new-cluster> to add future managed clusters without vendor involvement.

CARD: Final project sign-off & closeout

Acceptance criteria: Final sign-off and project closeout.